## Sheet1
LANDEN's Time-Frame Chart & Percent of standard draws required (For a standard construction contract)
| 2-3 weeks | 4-8 weeks | 2-4 weeks | 4-8 weeks | 3-4 weeks
| Pre-project process | Framing &Rough-ins | Drywall | Finishing | Completion
| Complementary design plans | Framing completed | Insulation | Millwork | Flooring install | How to Use this Calculator
| Finalized permit ready plans | HVAC rough-in | Boarding work | Cabinet install | Hardware | Fill-in the budget amount, (green B-21 cell) the calculator will auto fill
| Quoted price based on plans | Electrical rough-in | Tapping & Mud | Tile work | HVAC Final | If using an extra third draw (for larger projects) manually input
| Contract signing | Plumbing rough-in | Celling Texture | painting | Furnace clean | that number (green D-25 cell) and the forth draw will auto fill the difference
| Obtain all Permits | Selections by client | Priming | Electrical final | Paint touch-up | You will note that the 10 % Lien hold back auto fills, and
| Verify financing | Client extras rough-in | Order fixtures | Plumbing finish | Final clean | sets the payment for the lien hold back to pay out in 45 days later
|  | Rough-in inspections | Order materials | City inspections | City inspections | NOTE:
| 10% of budget due @ | Landen inspection | Landen inspection | Landen inspection | Landen inspection | This calculator is for helping you to set a rough budget &
| Completion of Permits | 35% of contract due | Optional Draw | 45% of contract due | 10% Balance Due | schedule of payments for cash-flow budgeting only
Some conditions may apply depending on project complexity and size
NOTE: THERE IS NO UPFRONT DEPOSIT, YOU ONLY PAY WHEN SERVICES ARE PROVIDED
Furthermore, each draw stage has a 10% Lien hold back held in the lawyers trust account for 45 Days
Amount of base budget
or contract Amount
| 750555 |  |  | Normal draw
|  |  | Optional | 45% |  | Note: Lien Hold back held in trust
| First draw | Second Draw | Third draw | Forth Draw | Final Draw |  | Totals
Draw % | 10% | 35% | 0% | 45% | 10%
Draw totals | 75055.5 | 262694.25 | 0 | 337749.75 | 75055.5 | Total draws | 750555 | Before Lien hold backs
Lien Holdback 10% | 7505.55 | 26269.425 | 0 | 33774.975 | 7505.55 | Total holdback | 75055.5 | Paid 45 days after each hold back date
Net advance | 67549.95 | 236424.825 | 0 | 303974.775 | 67549.95 | Total Net | 675499.5 | After Lien hold back's
Payout holdback 45 days |  | 7505.55 | 26269.425 | 0 | 33774.975 | 7505.55
Net with hold back | 67549.95 | 243930.375 | 26269.425 | 303974.775 | 101324.925 | 7505.55 | 750555
NOTE: See also our E-book "On how to protect yourself from Liens"