## Sheet1
Residential Construction Schedule Template (COPYRIGHT PROTECTED) "for Landen Client use only"
|  | For: Mr. & Mrs. | [11 empty] | mm/dd/yyyy
|  | PROJECT TYPE: New home build | [11 empty] | DATE
|  | JOB NUMBER: |  |  | 313 |  |  | Contract amount | 750000 | GST | 37500 | 787500
|  | PROJECT LOCATION: | [11 empty] | PAGE 1
LandenDevelopment.com
Task No. | Task Name |  |  | # of days |  | Start Date |  | End Date | Actual Completion | Variance (In Days) | Name of contractor | Remarks
[5 empty] | start |  | Fin |  |  |  | Supplier
| CRITICAL PATH ITEMS IN DARK BLUE * |  |  | Req. | day |  | day |  | Date |  | Or person responsible
| PHASE ONE - PLANNING & START-UP |  |  |  |  | First Start Date
1 | Close on Land building site purchase |  |  | 1 | Wed | 2020-10-07 | Thu | 2020-10-08 | 2020-10-08 | 0 | By Owner
2 | Verify Construction Funding |  |  | 1 | Wed | 2020-10-07 | Thu | 2020-10-08 | 2020-10-08 | 0 | By Owner
3 | Architectural planning |  |  | 14 | Thu | 2020-10-08 | Thu | 2020-10-22 | 2020-10-24 | -2 | By Landen
4 | Structural Drawings |  |  | 18 | Thu | 2020-10-22 | Mon | 2020-11-09 |  | 69 | By Landen
5 | Set detailed building specifications |  |  | 3 | Mon | 2020-11-09 | Thu | 2020-11-12 |  | 72 | By Landen
6 | Have Client make all selections |  |  | 7 | Thu | 2020-11-12 | Thu | 2020-11-19 |  | 79 | By Landen
7 | Client approves plans, spec's, and budget |  |  | 3 | Thu | 2020-11-19 | Sun | 2020-11-22 |  | 82 | By Owner
8 | Make any requested plan & spec's changes |  |  | 10 | Thu | 2020-11-26 | Sun | 2020-12-06 |  | 96 | By Landen
9 | Modify plans & spec's to meet any revisions |  |  | 5 | Sun | 2020-12-06 | Fri | 2020-12-11 |  | 101 | By Landen
PHASE TWO - TENDER-BIDS & CONTRACTS
10 | Make copies of all plans & spec's |  |  | 1 | Fri | 2020-12-11 | Sat | 2020-12-12 |  | 102 | By Landen
11 | Distribute plans & spec's to trades & suppliers |  |  | 5 | Sat | 2020-12-12 | Thu | 2020-12-17 |  | 107 | By Landen
12 | Tender project / quotes |  |  | 15 | Thu | 2020-12-17 | Fri | 2021-01-01 |  | 122 | By Landen
13 | Review Tenders & bids / quotes |  |  | 5 | Fri | 2021-01-01 | Wed | 2021-01-06 |  | 127 | By Landen
14 | Approve construction budget / quote |  |  | 3 | Fri | 2021-01-01 | Mon | 2021-01-04 | 2020-11-18 | 47 | By Owner | Delay in inspection notification
15 | Execute Subcontractor agreements |  |  | 4 | Mon | 2021-01-04 | Fri | 2021-01-08 | 2020-11-24 | 45 | By Landen
16 | Walk lot with owner before construction |  |  | 1 | Mon | 2021-01-04 | Tue | 2021-01-05 | 2020-11-17 | 49 | Owner / Landen
| UPFRONT DEPOIST DRAW |  |  | 15% | [7 empty] | 112500 | 5% | GST | 5625
[14 empty] | Total Draw | 118125
PHASE THREE - APPROVING ATHOURITIES
17 | Apply for Development Permits? |  | * | 0 | Fri | 2020-12-11 | Fri | 2020-12-11 |  | 101 | By Landen
18 | APPLY FOR BUILDING PERMITS |  | * | 15 | Fri | 2020-12-11 | Sat | 2020-12-26 | 2020-11-12 | 44 | By Landen
19 | BUILDING PERMIT APPROVALS |  | * | 1 | Sat | 2020-12-26 | Sun | 2020-12-27 |  | 117 | By Landen
20 | Construction liabilty insurance |  |  | 1 | Sun | 2020-12-27 | Mon | 2020-12-28 |  | 118 | By Landen
21 | Order window package |  |  | 1 | Sat | 2020-12-26 | Sun | 2020-12-27 |  | 117 | By Landen
22 | Order roof trusses & floor joist |  |  | 1 | Sat | 2020-12-26 | Sun | 2020-12-27 |  | 117 | By Landen
23 | Get lumber order ready |  |  | 1 | Sat | 2020-12-26 | Sun | 2020-12-27 |  | 117 | By Landen
24 | Schedule Surveyor |  |  | 1 | Sat | 2020-12-26 | Sun | 2020-12-27 |  | 117 | By Landen
25 | Schedule excavation |  |  | 1 | Sat | 2020-12-26 | Sun | 2020-12-27 |  | 117 | By Landen
26 | Prep building site "Clearing or strip top-soil" |  |  | 3 | Sat | 2020-12-26 | Tue | 2020-12-29 |  | 119 | By Landen
27 | Select & Schedule cribbing crew |  |  | 1 | Sat | 2020-12-26 | Sun | 2020-12-27 |  | 117 | By Landen
28 | Select & schedule framing crew |  |  | 1 | Sat | 2020-12-26 | Sun | 2020-12-27 |  | 117 | By Landen
PHASE FOUR - SITE PREP
29 | Clear lot of top soils / tress etc. (stock pile loam) |  | * | 2 | Sun | 2020-12-27 | Tue | 2020-12-29 | 2020-11-14 | 45 | Rockglen Excavate
30 | Surveyor pin site for excavation |  | * | 1 | Tue | 2020-12-29 | Wed | 2020-12-30 |  | 120 | Geodetic
31 | Excavate site |  | * | 3 | Wed | 2020-12-30 | Sat | 2021-01-02 |  | 123 | Rockglen Excavate
32 | Excavate sewer & Water |  |  | 1 | Sat | 2021-01-02 | Sun | 2021-01-03 |  | 124 | Rockglen Excavate
33 | Excavate electrical service |  |  | 1 | Sun | 2021-01-03 | Mon | 2021-01-04 |  | 125 | Rockglen Excavate
34 | Surveyor pin excavation for footings |  | * | 1 | Sat | 2021-01-02 | Sun | 2021-01-03 |  | 124 | Geodetic
35 | Deliver Lumber and rebar for foundation work |  |  | 1 | Sun | 2021-01-03 | Mon | 2021-01-04 |  | 125 | Dick's lumber
36 | Hook-up Temporary construction power |  |  | 1 | Mon | 2021-01-04 | Tue | 2021-01-05 |  | 126 | BDW Electric
PHASE FIVE - FOUNDATION
37 | Install footing forms |  |  | 3 | Sun | 2021-01-03 | Wed | 2021-01-06 |  | 127 | CAN Cribbing
38 | Inspect footings |  |  | 1 | Wed | 2021-01-06 | Thu | 2021-01-07 |  | 128 | By Landen
39 | Order concrete & pump for footing pour |  |  | 1 | Thu | 2021-01-07 | Fri | 2021-01-08 |  | 129 | Burnco
40 | Surveyor to pin top of footing |  |  | 1 | Fri | 2021-01-08 | Sat | 2021-01-09 |  | 130 | Geodetic
41 | Install foundation forms |  |  | 3 | Sat | 2021-01-09 | Tue | 2021-01-12 |  | 133 | CAN Cribbing
42 | Order concrete & pump for wall pour |  |  | 1 | Tue | 2021-01-12 | Wed | 2021-01-13 |  | 134 | Burnco
43 | Concrete pour foundation |  |  | 2 | Tue | 2021-01-12 | Thu | 2021-01-14 |  | 135 | Burnco
44 | Strip foundation |  |  | 1 | Thu | 2021-01-14 | Fri | 2021-01-15 |  | 136 | CAN Cribbing
45 | Order and install foundation seal |  |  | 1 | Fri | 2021-01-15 | Sat | 2021-01-16 |  | 137 | Spray Tar cont
46 | Foundation drainage gravel & weeping tile |  |  | 1 | Sat | 2021-01-16 | Sun | 2021-01-17 |  | 138 | A-1 Cement
47 | Foundation inspection by approving authorities |  |  | 2 | Sun | 2021-01-17 | Tue | 2021-01-19 |  | 140 | Approving Authorities
48 | Install sewer, water, and electrical service |  |  | 2 | Sat | 2021-01-16 | Mon | 2021-01-18 |  | 139 | A&S, Quigley Eject
49 | Install main electric panel c/w with temp power outlets |  |  | 1 | Fri | 2021-01-15 | Sat | 2021-01-16 |  | 137 | BDW elect
50 | Inspection of service installations |  |  | 1 | Sat | 2021-01-16 | Sun | 2021-01-17 |  | 138 | Approving Authorities
| FOUNDATION DRAW |  |  | 15% | [7 empty] | 112500 | 5% | GST | 5625
[14 empty] | Total Draw | 118125
51 | Back-fill foundation |  | * | 2 | Sun | 2021-01-17 | Tue | 2021-01-19 |  | 140 | Rockglen Excavate |  |  |  | Page 2
52 | Order main lumber package |  |  | 1 | Tue | 2021-01-19 | Wed | 2021-01-20 |  | 141 | Landen
53 | Order Garbage bin to site |  |  | 1 | Wed | 2021-01-20 | Thu | 2021-01-21 |  | 142 | PT Waste
54 | Order Porta-can toilet to site |  |  | 1 | Thu | 2021-01-21 | Fri | 2021-01-22 |  | 143 | CAN T ent
55 | Select and schedule fire place contractor |  |  | 1 | Tue | 2021-01-19 | Wed | 2021-01-20 |  | 141 | By Landen
56 | Select and schedule roofing contractor |  |  | 1 | Tue | 2021-01-19 | Wed | 2021-01-20 |  | 141 | By Landen
57 | Select and schedule siding contractor |  |  | 1 | Tue | 2021-01-19 | Wed | 2021-01-20 |  | 141 | By Landen
58 | Select and schedule soffit & gutter contractor |  |  | 1 | Tue | 2021-01-19 | Wed | 2021-01-20 |  | 141 | By Landen
59 | Select and schedule Plumbing Contractor |  |  | 1 | Tue | 2021-01-19 | Wed | 2021-01-20 |  | 141 | By Landen
60 | Select and schedule HVAC contractor |  |  | 1 | Tue | 2021-01-19 | Wed | 2021-01-20 |  | 141 | By Landen
61 | Select and schedule Electrical contractor |  |  | 1 | Tue | 2021-01-19 | Wed | 2021-01-20 |  | 141 | By Landen
62 | Select & schedule Insulation & drywall contractor |  |  | 1 | Tue | 2021-01-19 | Wed | 2021-01-20 |  | 141 | By Landen
63 | Select and schedule Vacuum contractor |  |  | 1 | Tue | 2021-01-19 | Wed | 2021-01-20 |  | 141 | By Landen
PHASE SIX - MAIN BUILDING STRUCTUER
64 | Deliver framing lumber package |  |  | 1 | Sat | 2021-01-23 | Sun | 2021-01-24 |  | 145 | Dick's lumber
65 | Start framing crew |  |  | 4 | Sun | 2021-01-24 | Thu | 2021-01-28 |  | 149 | M-Tech
66 | Main sub floor completed |  |  | 4 | Thu | 2021-01-28 | Mon | 2021-02-01 |  | 153 | M-Tech
67 | Main floor walls completed |  |  | 5 | Mon | 2021-02-01 | Sat | 2021-02-06 |  | 158 | M-Tech
68 | Deliver roof trusses |  |  | 1 | Sat | 2021-02-06 | Sun | 2021-02-07 |  | 159 | Dick's lumber
69 | Second floor sub floor completed |  |  | 4 | Sun | 2021-02-07 | Thu | 2021-02-11 |  | 163 | M-Tech
70 | Order stairs |  |  | 1 | Thu | 2021-02-11 | Fri | 2021-02-12 |  | 164 | By Landen
71 | Second floor walls completed |  |  | 5 | Fri | 2021-02-12 | Wed | 2021-02-17 |  | 169 | M-Tech
72 | Deliver windows and ex doors |  |  | 1 | Wed | 2021-02-17 | Thu | 2021-02-18 |  | 170 | Lux Windows
73 | Order garage overhead doors |  |  | 1 | Thu | 2021-02-18 | Fri | 2021-02-19 |  | 171 | Glenmore Door
74 | Deliver & Install stairs |  |  | 2 | Fri | 2021-02-19 | Sun | 2021-02-21 |  | 173 | Brydon
75 | HVAC mark-out |  |  | 3 | Sun | 2021-02-21 | Wed | 2021-02-24 |  | 176 | A&S Mechanical
76 | Cut-out HVAC holes by framer |  |  | 4 | Wed | 2021-02-24 | Sun | 2021-02-28 |  | 180 | M-Tech
77 | Framing roof on lock-up stage |  | * | 10 | Sun | 2021-02-28 | Wed | 2021-03-10 |  | 190 | M-Tech
78 | Prep & Pour basement concrete slab (See R-in-fl-heat) |  |  | 4 | Wed | 2021-03-10 | Sun | 2021-03-14 |  | 194 | A-1 Cement
79 | Framing basement development |  |  | 8 | Sun | 2021-03-14 | Mon | 2021-03-22 |  | 202 | M-Tech
80 | Framing inspections & engineering inspections |  |  | 3 | Mon | 2021-03-22 | Thu | 2021-03-25 |  | 205 | Approving Authorities
| LOCK-UP STAGE DRAW |  |  | 30% | [7 empty] | 225000 | 5% | GST | 11250
[14 empty] | Total Draw | 236250
PHASE SEVEN - MECANICAL ROUGH-IN
81 | Do electrical walk-through with owner |  |  | 1 | Thu | 2021-03-25 | Fri | 2021-03-26 |  | 206 | By Landen
82 | Install rough-in plumbing (FIRST order) |  |  | 4 | Fri | 2021-03-26 | Tue | 2021-03-30 |  | 210 | A&S Mechanical
83 | Install rough-in HVAC (SECOND order) |  |  | 4 | Tue | 2021-03-30 | Sat | 2021-04-03 |  | 214 | A&S Mechanical
84 | Install fire place's (rough-in) |  |  | 1 | Sat | 2021-04-03 | Sun | 2021-04-04 |  | 215 | Diamond FP
85 | Install rough-in electrical & media systems (THIRD order) |  |  | 4 | Sun | 2021-04-04 | Thu | 2021-04-08 |  | 219 | Diamond FP
86 | Install rough-in central vacuum (After electrical) |  |  | 1 | Thu | 2021-04-08 | Fri | 2021-04-09 |  | 220 | BDW elect
87 | Install security rough-ins |  |  | 2 | Fri | 2021-04-09 | Sun | 2021-04-11 |  | 222 | BDW elect
88 | Alarm rough-ins |  |  | 1 | Sun | 2021-04-11 | Mon | 2021-04-12 |  | 223 | BDW elect
89 | Set up for temporary heat (winter construction) |  |  | 1 | Mon | 2021-04-12 | Tue | 2021-04-13 |  | 224 | A&S Mechanical
90 | Rough-in mechanical inspections |  | * | 3 | Tue | 2021-04-13 | Fri | 2021-04-16 |  | 227 | Approving Authorities
91 | Final framing check and adjustments |  |  | 3 | Fri | 2021-04-16 | Mon | 2021-04-19 |  | 230 | By Landen
PHASE EHIGHT - EXTERIOR FINISHES
92 | Install roofing |  | * | 4 | Sun | 2021-04-04 | Thu | 2021-04-08 |  | 219
93 | Build decks & deck railing |  |  | 6 | Sun | 2021-04-04 | Sat | 2021-04-10 |  | 221 | M-Tech
94 | Install garage concrete slab |  |  | 1 | Sun | 2021-04-04 | Mon | 2021-04-05 |  | 216 | A-1 Cement
95 | Install exterior masonry / cultured stone |  |  | 6 | Sun | 2021-04-04 | Sat | 2021-04-10 |  | 221 | A-1 Cement
96 | Install exterior soffit & facia |  |  | 2 | Sun | 2021-04-04 | Tue | 2021-04-06 |  | 217 | ROB exteriors
97 | Install exterior siding, trim / stucco |  |  | 7 | Tue | 2021-04-06 | Tue | 2021-04-13 |  | 224 | ROB exteriors
98 | Paint exterior trim |  |  | 3 | Tue | 2021-04-13 | Fri | 2021-04-16 |  | 227 | A-J's Paint
99 | Install garage over head doors & openers |  |  | 3 | Fri | 2021-04-09 | Mon | 2021-04-12 |  | 223 | Glenmore Door
100 | Install drive way / patio concrete slab |  |  | 3 | Mon | 2021-04-12 | Thu | 2021-04-15 |  | 226 | A-1 Cement
101 | Select and schedule cabinets |  |  | 1 | Mon | 2021-04-12 | Tue | 2021-04-13 |  | 224 | Landen custom built
102 | Select and schedule finishing crew |  |  | 1 | Mon | 2021-04-12 | Tue | 2021-04-13 |  | 224 | Landen custom built
103 | Select and schedule int. railing installer |  |  | 1 | Mon | 2021-04-12 | Tue | 2021-04-13 |  | 224 | Landen custom built
104 | Select and schedule int. flooring contractors |  |  | 1 | Mon | 2021-04-12 | Tue | 2021-04-13 |  | 224 | All Floors
PHASE NINE - DRYWALL STAGE
105 | Install batt insulation & VB |  |  | 3 | Mon | 2021-04-19 | Thu | 2021-04-22 |  | 233 | Camber Drywall
106 | Caulk & air-seal, draft & fire stop |  |  | 1 | Thu | 2021-04-22 | Fri | 2021-04-23 |  | 234 | Camber Drywall
107 | Insulation inspection (before cover-up) |  |  | 1 | Fri | 2021-04-23 | Sat | 2021-04-24 |  | 235 | Camber Drywall
108 | Install drywall board |  |  | 5 | Sat | 2021-04-24 | Thu | 2021-04-29 |  | 240 | Camber Drywall
109 | Install blow-in attic insulation |  |  | 1 | Thu | 2021-04-29 | Fri | 2021-04-30 |  | 241 | Camber Drywall
110 | Order and schedule millwork packaged |  |  | 1 | Fri | 2021-04-30 | Sat | 2021-05-01 |  | 242 | Regal Building products
111 | Select and schedule painting contractor |  |  | 1 | Sat | 2021-05-01 | Sun | 2021-05-02 |  | 243 | A-J's Paint
112 | Drywall mud & tapping |  |  | 6 | Fri | 2021-04-30 | Thu | 2021-05-06 |  | 247 | Camber Drywall
113 | Drywall sanding |  |  | 1 | Thu | 2021-05-06 | Fri | 2021-05-07 |  | 248 | Camber Drywall
114 | Texture ceiling or level 5 ceiling |  |  | 1 | Fri | 2021-05-07 | Sat | 2021-05-08 |  | 249 | Camber Drywall
115 | Prime paint drywall |  | * | 1 | Sat | 2021-05-08 | Sun | 2021-05-09 |  | 250 | A-J's Paint
116 | Select and order appliances |  |  | 1 | Sat | 2021-05-08 | Sun | 2021-05-09 |  | 250 | Bow West App
117 | Select and order lighting fixtures |  |  | 1 | Sat | 2021-05-08 | Sun | 2021-05-09 |  | 250 | Signature Lighting
Page 3
| DRYWALL COMPLETE DRAW |  |  | 25% | [7 empty] | 187500 | 5% | GST | 9375
[14 empty] | Total Draw | 196875
PHASE TEN - INTERIOR FINIDHING STAGE
118 | Select and order all ceramic tile |  |  | 1 | Sun | 2021-05-09 | Mon | 2021-05-10 |  | 251 | Aimes Tile
119 | Deliver int. Millwork Package |  |  | 1 | Sun | 2021-05-09 | Mon | 2021-05-10 |  | 251 | Regal Building products
120 | Install millwork & finish carpentry |  |  | 14 | Mon | 2021-05-10 | Mon | 2021-05-24 |  | 265 | Landen custom crew
121 | Install int. railing |  |  | 4 | Mon | 2021-05-10 | Fri | 2021-05-14 |  | 255 | Landen custom crew
122 | Install cabinets |  |  | 6 | Mon | 2021-05-10 | Sun | 2021-05-16 |  | 257 | Landen custom crew
123 | Template and order counter tops |  |  | 2 | Sun | 2021-05-16 | Tue | 2021-05-18 |  | 259 | Granite City
124 | Install counter tops |  |  | 2 | Fri | 2021-05-28 | Sun | 2021-05-30 |  | 271 | Granite City
125 | Install wall and floor ceramic tile |  |  | 5 | Sun | 2021-05-30 | Fri | 2021-06-04 |  | 276 | Granite City
126 | Order shower enclosures |  |  | 1 | Fri | 2021-06-04 | Sat | 2021-06-05 |  | 277 | Tile Tech
127 | Drywall touch-up for painter |  |  | 1 | Sat | 2021-06-05 | Sun | 2021-06-06 |  | 278 | Camber Drywall
128 | Painting interior millwork & walls |  |  | 10 | Sun | 2021-06-06 | Wed | 2021-06-16 |  | 288 | A-J's Paint
PHASE ELEVIN - FINAL STAGE
129 | Install bathroom flooring |  |  | 3 | Wed | 2021-06-16 | Sat | 2021-06-19 |  | 291 | All Floors
130 | Install plumbing finishes / toilets |  |  | 2 | Sat | 2021-06-19 | Mon | 2021-06-21 |  | 293 | A&S Mechanical
131 | Install electrical finishes & lighting |  |  | 2 | Sat | 2021-06-19 | Mon | 2021-06-21 |  | 293 | BDW elect
132 | Install vac machine & cover plates |  |  | 1 | Sat | 2021-06-19 | Sun | 2021-06-20 |  | 292 | Vac-flow
133 | Install media systems finishes |  |  | 2 | Sat | 2021-06-19 | Mon | 2021-06-21 |  | 293 | BDW elect
134 | Install shower glass & mirrors |  |  | 3 | Mon | 2021-06-07 | Thu | 2021-06-10 |  | 282 | Edge Works Glass
135 | Install door & bath hardware |  |  | 1 | Wed | 2021-06-16 | Thu | 2021-06-17 |  | 289 | Landen custom crew
136 | Install floor finishes carpet / hardwood |  |  | 6 | Wed | 2021-06-16 | Tue | 2021-06-22 |  | 294 | All Floors
137 | Deliver appliances |  |  | 1 | Tue | 2021-06-22 | Wed | 2021-06-23 |  | 295 | Supplier
138 | Baseboard other installation |  |  | 2 | Tue | 2021-06-22 | Thu | 2021-06-24 |  | 296 | Carpentry Team
139 | Install appliances |  |  | 2 | Wed | 2021-06-23 | Fri | 2021-06-25 |  | 297 | Installation Team
140 | Final Plumbing & HVAC inspections |  |  | 2 | Wed | 2021-06-23 | Fri | 2021-06-25 |  | 297 | Electrical Team
141 | Final Electrical inspections |  |  | 2 | Wed | 2021-06-23 | Fri | 2021-06-25 |  | 297 | Approving Authorities
142 | Rough initial home clean |  |  | 1 | Fri | 2021-06-25 | Sat | 2021-06-26 |  | 298 | All pro cleaners
143 | Furnace duct cleaning |  |  | 1 | Sat | 2021-06-26 | Sun | 2021-06-27 |  | 299 | Action Furnace
144 | Final home clean |  |  | 1 | Sun | 2021-06-27 | Mon | 2021-06-28 |  | 300 | All pro cleaners
PHASE TWELVE FINAL EXTERIOR WORK
145 | Final grade |  |  | 2 | Fri | 2021-06-25 | Sun | 2021-06-27 |  | 299 | Rockglen Excavate
146 | Patios & Sidewalks |  |  | 3 | Sun | 2021-06-27 | Wed | 2021-06-30 |  | 302 | A-1 Cement
147 | Trees & shrubs installed |  |  | 3 | Wed | 2021-06-30 | Sat | 2021-07-03 |  | 305 | Michel's Land Scaping
148 | Top-soil-Loam |  |  | 2 | Sat | 2021-07-03 | Mon | 2021-07-05 |  | 307 | Rockglen Excavate
149 | Grass seed / sod |  |  | 2 | Mon | 2021-07-05 | Wed | 2021-07-07 |  | 309 | Michel's Land Scaping
150 | Fencing |  |  | 3 | Sun | 2021-06-27 | Wed | 2021-06-30 |  | 302 | Michel's Land Scaping
| FINAL COMPLETE HOME DRAW |  |  | 15% | [7 empty] | 112500 | 5% | GST | 5625
|  |  |  | 100% | [9 empty] | Total Draw | 118125
[13 empty] | Total with GST |  | 787500
TURN OVER TO CLIENT
151 | Notice of substantial complete posted |  | * | 1 | Mon | 2021-06-28 | Tue | 2021-06-29 |  | 301 | By Landen
152 | Final occupancy inspection by approving authorities |  |  | 1 | Tue | 2021-06-29 | Wed | 2021-06-30 |  | 302 | Approving Authorities
153 | New Home Warranty inspections |  |  | 1 | Wed | 2021-06-30 | Thu | 2021-07-01 |  | 303 | National Warranty
154 | Lien hold back time started |  |  | 1 | Thu | 2021-07-01 | Fri | 2021-07-02 |  | 304 | By Landen
155 | Punch list inspection done |  |  | 1 | Fri | 2021-07-02 | Sat | 2021-07-03 |  | 305 | By Landen
156 | Final service work and punch list completed |  |  | 7 | Sat | 2021-07-03 | Sat | 2021-07-10 |  | 312 | By Landen
MOVE-IN
[8 empty] | Total Project Days | 276 | Inc. week-ends
|  |  |  | NOTE: Adjust # of days req for week-ends |  |  |  | Total Project Months | 9.2
How to use this LANDEN Project Schedule Template
First, fill in the "Yellow Cell" G12 with the start date, the template will then auto fill a "standard schedule" based on an average custom home's time for construction
Second, adjust the number of days for each/every task in column 'E" the end date for each task will then about-fill in column I, and move the balance of the schedule to match
Third, adjust schedule for "week-ends" the auto fill function does not take into account week-end days of Sat or Sun, simply add or subtract a day in column "G" for example, row 153 formula would be I201+2
NOTE: the RED cell E17 is optional for the possibility of a development permit (DP) this extra permit step is not always needed, however would add 30-60 days to the schedule.
NOTE: column J is where you enter the actual finished date "blue" then column K will auto-fill, black numbers = on or ahead of time, red numbers = NOT ON Schedule, and may require schedule adjustment!
NOTE: Rows highlighted in Dark Blue are "Critical Path" items that must be meet to keep the project on tract. Also notated by *
NOTE: Rows highlighted in Green are proposed funding draw dates, and are based on the contract input number in cell J5.
NOTE: Column L will auoto fill with first trade / supplier change.
Formulas:
End Date = [Start Date]+[Req.]
Actual Completion = [End Date]
Variance (In Days) = IF([Actual Completion]="",[End Date]-TODAY(),[End Date]-[Actual Completion])
Start Date = [Start Date, row above]
Start Date = [End Date, row above]

## Sheet2
| DAILY GANTT CHART | [5 empty] | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri
| For: Mr. & Mrs. |  |  |  | # of days |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 140 | 141 | 142 | 143 | 144 | 145 | 146 | 147 | 148 | 149 | 150 | 151 | 152 | 153 | 154 | 155 | 156 | 157 | 158 | 159 | 160 | 161 | 162 | 163 | 164 | 165 | 166 | 167 | 168 | 169 | 170 | 171 | 172 | 173 | 174 | 175 | 176 | 177 | 178 | 179 | 180 | 181 | 182 | 183 | 184 | 185 | 186 | 187 | 188 | 189 | 190 | 191 | 192 | 193 | 194 | 195 | 196 | 197 | 198 | 199 | 200 | 201 | 202 | 203 | 204 | 205 | 206 | 207 | 208 | 209 | 210 | 211 | 212 | 213 | 214 | 215 | 216 | 217 | 218 | 219 | 220 | 221 | 222 | 223 | 224 | 225 | 226 | 227 | 228 | 229 | 230 | 231 | 232 | 233 | 234 | 235 | 236 | 237 | 238 | 239 | 240 | 241 | 242 | 243 | 244 | 245 | 246 | 247 | 248 | 249 | 250 | 251 | 252 | 253 | 254 | 255 | 256 | 257 | 258 | 259 | 260 | 261 | 262 | 263 | 264 | 265 | 266 | 267 | 268 | 269 | 270 | 271 | 272 | 273 | 274 | 275 | 276 | 277 | 278 | 279 | 280 | 281 | 282 | 283 | 284 | 285 | 286 | 287 | 288 | 289 | 290 | 291 | 292 | 293 | 294 | 295 | 296 | 297 | 298 | 299 | 300 | 301 | 302 | 303 | 304
| PROJECT LOCATION: |  | Start Date | Duration | End Date | % Done | 2020-10-07 | 2020-10-08 | 2020-10-09 | 2020-10-10 | 2020-10-11 | 2020-10-12 | 2020-10-13 | 2020-10-14 | 2020-10-15 | 2020-10-16 | 2020-10-17 | 2020-10-18 | 2020-10-19 | 2020-10-20 | 2020-10-21 | 2020-10-22 | 2020-10-23 | 2020-10-24 | 2020-10-25 | 2020-10-26 | 2020-10-27 | 2020-10-28 | 2020-10-29 | 2020-10-30 | 2020-10-31 | 2020-11-01 | 2020-11-02 | 2020-11-03 | 2020-11-04 | 2020-11-05 | 2020-11-06 | 2020-11-07 | 2020-11-08 | 2020-11-09 | 2020-11-10 | 2020-11-11 | 2020-11-12 | 2020-11-13 | 2020-11-14 | 2020-11-15 | 2020-11-16 | 2020-11-17 | 2020-11-18 | 2020-11-19 | 2020-11-20 | 2020-11-21 | 2020-11-22 | 2020-11-23 | 2020-11-24 | 2020-11-25 | 2020-11-26 | 2020-11-27 | 2020-11-28 | 2020-11-29 | 2020-11-30 | 2020-12-01 | 2020-12-02 | 2020-12-03 | 2020-12-04 | 2020-12-05 | 2020-12-06 | 2020-12-07 | 2020-12-08 | 2020-12-09 | 2020-12-10 | 2020-12-11 | 2020-12-12 | 2020-12-13 | 2020-12-14 | 2020-12-15 | 2020-12-16 | 2020-12-17 | 2020-12-18 | 2020-12-19 | 2020-12-20 | 2020-12-21 | 2020-12-22 | 2020-12-23 | 2020-12-24 | 2020-12-25 | 2020-12-26 | 2020-12-27 | 2020-12-28 | 2020-12-29 | 2020-12-30 | 2020-12-31 | 2021-01-01 | 2021-01-02 | 2021-01-03 | 2021-01-04 | 2021-01-05 | 2021-01-06 | 2021-01-07 | 2021-01-08 | 2021-01-09 | 2021-01-10 | 2021-01-11 | 2021-01-12 | 2021-01-13 | 2021-01-14 | 2021-01-15 | 2021-01-16 | 2021-01-17 | 2021-01-18 | 2021-01-19 | 2021-01-20 | 2021-01-21 | 2021-01-22 | 2021-01-23 | 2021-01-24 | 2021-01-25 | 2021-01-26 | 2021-01-27 | 2021-01-28 | 2021-01-29 | 2021-01-30 | 2021-01-31 | 2021-02-01 | 2021-02-02 | 2021-02-03 | 2021-02-04 | 2021-02-05 | 2021-02-06 | 2021-02-07 | 2021-02-08 | 2021-02-09 | 2021-02-10 | 2021-02-11 | 2021-02-12 | 2021-02-13 | 2021-02-14 | 2021-02-15 | 2021-02-16 | 2021-02-17 | 2021-02-18 | 2021-02-19 | 2021-02-20 | 2021-02-21 | 2021-02-22 | 2021-02-23 | 2021-02-24 | 2021-02-25 | 2021-02-26 | 2021-02-27 | 2021-02-28 | 2021-03-01 | 2021-03-02 | 2021-03-03 | 2021-03-04 | 2021-03-05 | 2021-03-06 | 2021-03-07 | 2021-03-08 | 2021-03-09 | 2021-03-10 | 2021-03-11 | 2021-03-12 | 2021-03-13 | 2021-03-14 | 2021-03-15 | 2021-03-16 | 2021-03-17 | 2021-03-18 | 2021-03-19 | 2021-03-20 | 2021-03-21 | 2021-03-22 | 2021-03-23 | 2021-03-24 | 2021-03-25 | 2021-03-26 | 2021-03-27 | 2021-03-28 | 2021-03-29 | 2021-03-30 | 2021-03-31 | 2021-04-01 | 2021-04-02 | 2021-04-03 | 2021-04-04 | 2021-04-05 | 2021-04-06 | 2021-04-07 | 2021-04-08 | 2021-04-09 | 2021-04-10 | 2021-04-11 | 2021-04-12 | 2021-04-13 | 2021-04-14 | 2021-04-15 | 2021-04-16 | 2021-04-17 | 2021-04-18 | 2021-04-19 | 2021-04-20 | 2021-04-21 | 2021-04-22 | 2021-04-23 | 2021-04-24 | 2021-04-25 | 2021-04-26 | 2021-04-27 | 2021-04-28 | 2021-04-29 | 2021-04-30 | 2021-05-01 | 2021-05-02 | 2021-05-03 | 2021-05-04 | 2021-05-05 | 2021-05-06 | 2021-05-07 | 2021-05-08 | 2021-05-09 | 2021-05-10 | 2021-05-11 | 2021-05-12 | 2021-05-13 | 2021-05-14 | 2021-05-15 | 2021-05-16 | 2021-05-17 | 2021-05-18 | 2021-05-19 | 2021-05-20 | 2021-05-21 | 2021-05-22 | 2021-05-23 | 2021-05-24 | 2021-05-25 | 2021-05-26 | 2021-05-27 | 2021-05-28 | 2021-05-29 | 2021-05-30 | 2021-05-31 | 2021-06-01 | 2021-06-02 | 2021-06-03 | 2021-06-04 | 2021-06-05 | 2021-06-06 | 2021-06-07 | 2021-06-08 | 2021-06-09 | 2021-06-10 | 2021-06-11 | 2021-06-12 | 2021-06-13 | 2021-06-14 | 2021-06-15 | 2021-06-16 | 2021-06-17 | 2021-06-18 | 2021-06-19 | 2021-06-20 | 2021-06-21 | 2021-06-22 | 2021-06-23 | 2021-06-24 | 2021-06-25 | 2021-06-26 | 2021-06-27 | 2021-06-28 | 2021-06-29 | 2021-06-30 | 2021-07-01 | 2021-07-02 | 2021-07-03 | 2021-07-04 | 2021-07-05 | 2021-07-06 | 2021-07-07 | 2021-07-08 | 2021-07-09 | 2021-07-10 | 2021-07-11 | 2021-07-12 | 2021-07-13 | 2021-07-14 | 2021-07-15 | 2021-07-16 | 2021-07-17 | 2021-07-18 | 2021-07-19 | 2021-07-20 | 2021-07-21 | 2021-07-22 | 2021-07-23 | 2021-07-24 | 2021-07-25 | 2021-07-26 | 2021-07-27 | 2021-07-28 | 2021-07-29 | 2021-07-30 | 2021-07-31 | 2021-08-01 | 2021-08-02 | 2021-08-03 | 2021-08-04 | 2021-08-05 | 2021-08-06
PHASE ONE - PLANNING & START-UP
1 | Close on Land building site purchase |  | 2020-10-07 | 1 | 2020-10-08 | 25% | bar: Wed 1 to Thu 2
2 | Verify Construction Funding |  | 2020-10-07 | 1 | 2020-10-08 | 0% | bar: Wed 1 to Thu 2
3 | Architectural planning |  | 2020-10-08 | 14 | 2020-10-22 | 0% | bar: Thu 2 to Thu 16
4 | Structural Drawings |  | 2020-10-22 | 18 | 2020-11-09 | 0% | bar: Thu 16 to Mon 34
5 | Set detailed building specifications |  | 2020-11-09 | 3 | 2020-11-12 | 0% | bar: Mon 34 to Thu 37
6 | Have Client make all selections |  | 2020-11-12 | 7 | 2020-11-19 | 0% | bar: Thu 37 to Thu 44
7 | Client approves plans, spec's, and budget |  | 2020-11-19 | 3 | 2020-11-22 | 0% | bar: Thu 44 to Sun 47
8 | Make any requested plan & spec's changes |  | 2020-11-26 | 10 | 2020-12-06 | 0% | bar: Thu 51 to Sun 61
9 | Modify plans & spec's to meet any revisions |  | 2020-12-06 | 5 | 2020-12-11 | 0% | bar: Sun 61 to Fri 66
PHASE TWO - TENDER-BIDS & CONTRACTS
10 | Make copies of all plans & spec's |  | 2020-12-11 | 1 | 2020-12-12 | 0% | bar: Fri 66 to Sat 67
11 | Distribute plans & spec's to trades & suppliers |  | 2020-12-12 | 5 | 2020-12-17 | 0% | bar: Sat 67 to Thu 72
12 | Tender project / quotes |  | 2020-12-17 | 15 | 2021-01-01 | 0% | bar: Thu 72 to Fri 87
13 | Review Tenders & bids / quotes |  | 2021-01-01 | 5 | 2021-01-06 | 0% | bar: Fri 87 to Wed 92
14 | Approve construction budget / quote |  | 2021-01-01 | 3 | 2021-01-04 | 0% | bar: Fri 87 to Mon 90
15 | Execute Subcontractor agreements |  | 2021-01-04 | 4 | 2021-01-08 | 0% | bar: Mon 90 to Fri 94
16 | Walk lot with owner before construction |  | 2021-01-04 | 1 | 2021-01-05 | 0% | bar: Mon 90 to Tue 91
| UPFRONT DEPOIST DRAW |  | 2021-01-05 |  | 2021-01-05 | 0% | bar: Tue 91
PHASE THREE - APPROVING ATHOURITIES
17 | Apply for Development Permits? | * | 2020-12-11 | 0 | 2020-12-11 | 0% | bar: Fri 66
18 | APPLY FOR BUILDING PERMITS | * | 2020-12-11 | 15 | 2020-12-26 | 0% | bar: Fri 66 to Sat 81
19 | BUILDING PERMIT APPROVALS | * | 2020-12-26 | 1 | 2020-12-27 | 0% | bar: Sat 81 to Sun 82
20 | Construction liabilty insurance |  | 2020-12-27 | 1 | 2020-12-28 | 0% | bar: Sun 82 to Mon 83
21 | Order window package |  | 2020-12-26 | 1 | 2020-12-27 | 0% | bar: Sat 81 to Sun 82
22 | Order roof trusses & floor joist |  | 2020-12-26 | 1 | 2020-12-27 | 0% | bar: Sat 81 to Sun 82
23 | Get lumber order ready |  | 2020-12-26 | 1 | 2020-12-27 | 0% | bar: Sat 81 to Sun 82
24 | Schedule Surveyor |  | 2020-12-26 | 1 | 2020-12-27 | 0% | bar: Sat 81 to Sun 82
25 | Schedule excavation |  | 2020-12-26 | 1 | 2020-12-27 | 0% | bar: Sat 81 to Sun 82
26 | Prep building site "Clearing or strip top-soil" |  | 2020-12-26 | 3 | 2020-12-29 | 0% | bar: Sat 81 to Tue 84
27 | Select & Schedule cribbing crew |  | 2020-12-26 | 1 | 2020-12-27 | 0% | bar: Sat 81 to Sun 82
28 | Select & schedule framing crew |  | 2020-12-26 | 1 | 2020-12-27 | 0% | bar: Sat 81 to Sun 82
PHASE FOUR - SITE PREP
29 | Clear lot of top soils / tress etc. (stock pile loam) | * | 2020-12-27 | 2 | 2020-12-29 | 0% | bar: Sun 82 to Tue 84
30 | Surveyor pin site for excavation | * | 2020-12-29 | 1 | 2020-12-30 | 0% | bar: Tue 84 to Wed 85
31 | Excavate site | * | 2020-12-30 | 3 | 2021-01-02 | 0% | bar: Wed 85 to Sat 88
32 | Excavate sewer & Water |  | 2021-01-02 | 1 | 2021-01-03 | 0% | bar: Sat 88 to Sun 89
33 | Excavate electrical service |  | 2021-01-03 | 1 | 2021-01-04 | 0% | bar: Sun 89 to Mon 90
34 | Surveyor pin excavation for footings | * | 2021-01-02 | 1 | 2021-01-03 | 0% | bar: Sat 88 to Sun 89
35 | Deliver Lumber and rebar for foundation work |  | 2021-01-03 | 1 | 2021-01-04 | 0% | bar: Sun 89 to Mon 90
36 | Hook-up Temporary construction power |  | 2021-01-04 | 1 | 2021-01-05 | 0% | bar: Mon 90 to Tue 91
PHASE FIVE - FOUNDATION
37 | Install footing forms |  | 2021-01-03 | 3 | 2021-01-06 | 0% | bar: Sun 89 to Wed 92
38 | Inspect footings |  | 2021-01-06 | 1 | 2021-01-07 | 0% | bar: Wed 92 to Thu 93
39 | Order concrete & pump for footing pour |  | 2021-01-07 | 1 | 2021-01-08 | 0% | bar: Thu 93 to Fri 94
40 | Surveyor to pin top of footing |  | 2021-01-08 | 1 | 2021-01-09 | 0% | bar: Fri 94 to Sat 95
41 | Install foundation forms |  | 2021-01-09 | 3 | 2021-01-12 | 0% | bar: Sat 95 to Tue 98
42 | Order concrete & pump for wall pour |  | 2021-01-12 | 1 | 2021-01-13 | 0% | bar: Tue 98 to Wed 99
43 | Concrete pour foundation |  | 2021-01-12 | 2 | 2021-01-14 | 0% | bar: Tue 98 to Thu 100
44 | Strip foundation |  | 2021-01-14 | 1 | 2021-01-15 | 0% | bar: Thu 100 to Fri 101
45 | Order and install foundation seal |  | 2021-01-15 | 1 | 2021-01-16 | 0% | bar: Fri 101 to Sat 102
46 | Foundation drainage gravel & weeping tile |  | 2021-01-16 | 1 | 2021-01-17 | 0% | bar: Sat 102 to Sun 103
47 | Foundation inspection by approving authorities |  | 2021-01-17 | 2 | 2021-01-19 | 0% | bar: Sun 103 to Tue 105
48 | Install sewer, water, and electrical service |  | 2021-01-16 | 2 | 2021-01-18 | 0% | bar: Sat 102 to Mon 104
49 | Install main electric panel c/w with temp power outlets |  | 2021-01-15 | 1 | 2021-01-16 | 0% | bar: Fri 101 to Sat 102
50 | Inspection of service installations |  | 2021-01-16 | 1 | 2021-01-17 | 0% | bar: Sat 102 to Sun 103
| FOUNDATION DRAW |  | 2021-01-17 |  | 2021-01-17 | 0% | bar: Sun 103
51 | Back-fill foundation | * | 2021-01-17 | 2 | 2021-01-19 | 0% | bar: Sun 103 to Tue 105
52 | Order main lumber package |  | 2021-01-19 | 1 | 2021-01-20 | 0% | bar: Tue 105 to Wed 106
53 | Order Garbage bin to site |  | 2021-01-20 | 1 | 2021-01-21 | 0% | bar: Wed 106 to Thu 107
54 | Order Porta-can toilet to site |  | 2021-01-21 | 1 | 2021-01-22 | 0% | bar: Thu 107 to Fri 108
55 | Select and schedule fire place contractor |  | 2021-01-19 | 1 | 2021-01-20 | 0% | bar: Tue 105 to Wed 106
56 | Select and schedule roofing contractor |  | 2021-01-19 | 1 | 2021-01-20 | 0% | bar: Tue 105 to Wed 106
57 | Select and schedule siding contractor |  | 2021-01-19 | 1 | 2021-01-20 | 0% | bar: Tue 105 to Wed 106
58 | Select and schedule soffit & gutter contractor |  | 2021-01-19 | 1 | 2021-01-20 | 0% | bar: Tue 105 to Wed 106
59 | Select and schedule Plumbing Contractor |  | 2021-01-19 | 1 | 2021-01-20 | 0% | bar: Tue 105 to Wed 106
60 | Select and schedule HVAC contractor |  | 2021-01-19 | 1 | 2021-01-20 | 0% | bar: Tue 105 to Wed 106
61 | Select and schedule Electrical contractor |  | 2021-01-19 | 1 | 2021-01-20 | 0% | bar: Tue 105 to Wed 106
62 | Select & schedule Insulation & drywall contractor |  | 2021-01-19 | 1 | 2021-01-20 | 0% | bar: Tue 105 to Wed 106
63 | Select and schedule Vacuum contractor |  | 2021-01-19 | 1 | 2021-01-20 | 0% | bar: Tue 105 to Wed 106
PHASE SIX - MAIN BUILDING STRUCTUER
64 | Deliver framing lumber package |  | 2021-01-23 | 1 | 2021-01-24 | 0% | bar: Sat 109 to Sun 110
65 | Start framing crew |  | 2021-01-24 | 4 | 2021-01-28 | 0% | bar: Sun 110 to Thu 114
66 | Main sub floor completed |  | 2021-01-28 | 4 | 2021-02-01 | 0% | bar: Thu 114 to Mon 118
67 | Main floor walls completed |  | 2021-02-01 | 5 | 2021-02-06 | 0% | bar: Mon 118 to Sat 123
68 | Deliver roof trusses |  | 2021-02-06 | 1 | 2021-02-07 | 0% | bar: Sat 123 to Sun 124
69 | Second floor sub floor completed |  | 2021-02-07 | 4 | 2021-02-11 | 0% | bar: Sun 124 to Thu 128
70 | Order stairs |  | 2021-02-11 | 1 | 2021-02-12 | 0% | bar: Thu 128 to Fri 129
71 | Second floor walls completed |  | 2021-02-12 | 5 | 2021-02-17 | 0% | bar: Fri 129 to Wed 134
72 | Deliver windows and ex doors |  | 2021-02-17 | 1 | 2021-02-18 | 0% | bar: Wed 134 to Thu 135
73 | Order garage overhead doors |  | 2021-02-18 | 1 | 2021-02-19 | 0% | bar: Thu 135 to Fri 136
74 | Deliver & Install stairs |  | 2021-02-19 | 2 | 2021-02-21 | 0% | bar: Fri 136 to Sun 138
75 | HVAC mark-out |  | 2021-02-21 | 3 | 2021-02-24 | 0% | bar: Sun 138 to Wed 141
76 | Cut-out HVAC holes by framer |  | 2021-02-24 | 4 | 2021-02-28 | 0% | bar: Wed 141 to Sun 145
77 | Framing roof on lock-up stage | * | 2021-02-28 | 10 | 2021-03-10 | 0% | bar: Sun 145 to Wed 155
78 | Prep & Pour basement concrete slab (See R-in-fl-heat) |  | 2021-03-10 | 4 | 2021-03-14 | 0% | bar: Wed 155 to Sun 159
79 | Framing basement development |  | 2021-03-14 | 8 | 2021-03-22 | 0% | bar: Sun 159 to Mon 167
80 | Framing inspections & engineering inspections |  | 2021-03-22 | 3 | 2021-03-25 | 0% | bar: Mon 167 to Thu 170
| LOCK-UP STAGE DRAW |  | 2021-03-23 |  | 2021-03-23 | 0% | bar: Tue 168
PHASE SEVEN - MECANICAL ROUGH-IN
81 | Do electrical walk-through with owner |  | 2021-03-25 | 1 | 2021-03-26 | 0% | bar: Thu 170 to Fri 171
82 | Install rough-in plumbing (FIRST order) |  | 2021-03-26 | 4 | 2021-03-30 | 0% | bar: Fri 171 to Tue 175
83 | Install rough-in HVAC (SECOND order) |  | 2021-03-30 | 4 | 2021-04-03 | 0% | bar: Tue 175 to Sat 179
84 | Install fire place's (rough-in) |  | 2021-04-03 | 1 | 2021-04-04 | 0% | bar: Sat 179 to Sun 180
85 | Install rough-in electrical & media systems (THIRD order) |  | 2021-04-04 | 4 | 2021-04-08 | 0% | bar: Sun 180 to Thu 184
86 | Install rough-in central vacuum (After electrical) |  | 2021-04-08 | 1 | 2021-04-09 | 0% | bar: Thu 184 to Fri 185
87 | Install security rough-ins |  | 2021-04-09 | 2 | 2021-04-11 | 0% | bar: Fri 185 to Sun 187
88 | Alarm rough-ins |  | 2021-04-11 | 1 | 2021-04-12 | 0% | bar: Sun 187 to Mon 188
89 | Set up for temporary heat (winter construction) |  | 2021-04-12 | 1 | 2021-04-13 | 0% | bar: Mon 188 to Tue 189
90 | Rough-in mechanical inspections | * | 2021-04-13 | 3 | 2021-04-16 | 0% | bar: Tue 189 to Fri 192
91 | Final framing check and adjustments |  | 2021-04-16 | 3 | 2021-04-19 | 0% | bar: Fri 192 to Mon 195
PHASE EHIGHT - EXTERIOR FINISHES
92 | Install roofing | * | 2021-04-04 | 4 | 2021-04-08 | 0% | bar: Sun 180 to Thu 184
93 | Build decks & deck railing |  | 2021-04-04 | 6 | 2021-04-10 | 0% | bar: Sun 180 to Sat 186
94 | Install garage concrete slab |  | 2021-04-04 | 1 | 2021-04-05 | 0% | bar: Sun 180 to Mon 181
95 | Install exterior masonry / cultured stone |  | 2021-04-04 | 6 | 2021-04-10 | 0% | bar: Sun 180 to Sat 186
96 | Install exterior soffit & facia |  | 2021-04-04 | 2 | 2021-04-06 | 0% | bar: Sun 180 to Tue 182
97 | Install exterior siding, trim / stucco |  | 2021-04-06 | 7 | 2021-04-13 | 0% | bar: Tue 182 to Tue 189
98 | Paint exterior trim |  | 2021-04-13 | 3 | 2021-04-16 | 0% | bar: Tue 189 to Fri 192
99 | Install garage over head doors & openers |  | 2021-04-09 | 3 | 2021-04-12 | 0% | bar: Fri 185 to Mon 188
100 | Install drive way / patio concrete slab |  | 2021-04-12 | 3 | 2021-04-15 | 0% | bar: Mon 188 to Thu 191
101 | Select and schedule cabinets |  | 2021-04-12 | 1 | 2021-04-13 | 0% | bar: Mon 188 to Tue 189
102 | Select and schedule finishing crew |  | 2021-04-12 | 1 | 2021-04-13 | 0% | bar: Mon 188 to Tue 189
103 | Select and schedule int. railing installer |  | 2021-04-12 | 1 | 2021-04-13 | 0% | bar: Mon 188 to Tue 189
104 | Select and schedule int. flooring contractors |  | 2021-04-12 | 1 | 2021-04-13 | 0% | bar: Mon 188 to Tue 189
PHASE NINE - DRYWALL STAGE
105 | Install batt insulation & VB |  | 2021-04-19 | 3 | 2021-04-22 | 0% | bar: Mon 195 to Thu 198
106 | Caulk & air-seal, draft & fire stop |  | 2021-04-22 | 1 | 2021-04-23 | 0% | bar: Thu 198 to Fri 199
107 | Insulation inspection (before cover-up) |  | 2021-04-23 | 1 | 2021-04-24 | 0% | bar: Fri 199 to Sat 200
108 | Install drywall board |  | 2021-04-24 | 5 | 2021-04-29 | 0% | bar: Sat 200 to Thu 205
109 | Install blow-in attic insulation |  | 2021-04-29 | 1 | 2021-04-30 | 0% | bar: Thu 205 to Fri 206
110 | Order and schedule millwork packaged |  | 2021-04-30 | 1 | 2021-05-01 | 0% | bar: Fri 206 to Sat 207
111 | Select and schedule painting contractor |  | 2021-05-01 | 1 | 2021-05-02 | 0% | bar: Sat 207 to Sun 208
112 | Drywall mud & tapping |  | 2021-04-30 | 6 | 2021-05-06 | 0% | bar: Fri 206 to Thu 212
113 | Drywall sanding |  | 2021-05-06 | 1 | 2021-05-07 | 0% | bar: Thu 212 to Fri 213
114 | Texture ceiling or level 5 ceiling |  | 2021-05-07 | 1 | 2021-05-08 | 0% | bar: Fri 213 to Sat 214
115 | Prime paint drywall | * | 2021-05-08 | 1 | 2021-05-09 | 0% | bar: Sat 214 to Sun 215
116 | Select and order appliances |  | 2021-05-08 | 1 | 2021-05-09 | 0% | bar: Sat 214 to Sun 215
117 | Select and order lighting fixtures |  | 2021-05-08 | 1 | 2021-05-09 | 0% | bar: Sat 214 to Sun 215
| DRYWALL COMPLETE DRAW |  | 2021-05-09 |  | 2021-05-09 | 0% | bar: Sun 215
PHASE TEN - INTERIOR FINIDHING STAGE
118 | Select and order all ceramic tile |  | 2021-05-09 | 1 | 2021-05-10 | 0% | bar: Sun 215 to Mon 216
119 | Deliver int. Millwork Package |  | 2021-05-09 | 1 | 2021-05-10 | 0% | bar: Sun 215 to Mon 216
120 | Install millwork & finish carpentry |  | 2021-05-10 | 14 | 2021-05-24 | 0% | bar: Mon 216 to Mon 230
121 | Install int. railing |  | 2021-05-10 | 4 | 2021-05-14 | 0% | bar: Mon 216 to Fri 220
122 | Install cabinets |  | 2021-05-10 | 6 | 2021-05-16 | 0% | bar: Mon 216 to Sun 222
123 | Template and order counter tops |  | 2021-05-16 | 2 | 2021-05-18 | 0% | bar: Sun 222 to Tue 224
124 | Install counter tops |  | 2021-05-28 | 2 | 2021-05-30 | 0% | bar: Fri 234 to Sun 236
125 | Install wall and floor ceramic tile |  | 2021-05-30 | 5 | 2021-06-04 | 0% | bar: Sun 236 to Fri 241
126 | Order shower enclosures |  | 2021-06-04 | 1 | 2021-06-05 | 0% | bar: Fri 241 to Sat 242
127 | Drywall touch-up for painter |  | 2021-06-05 | 1 | 2021-06-06 | 0% | bar: Sat 242 to Sun 243
128 | Painting interior millwork & walls |  | 2021-06-06 | 10 | 2021-06-16 | 0% | bar: Sun 243 to Wed 253
PHASE ELEVIN - FINAL STAGE
129 | Install bathroom flooring |  | 2021-06-16 | 3 | 2021-06-19 | 0% | bar: Wed 253 to Sat 256
130 | Install plumbing finishes / toilets |  | 2021-06-19 | 2 | 2021-06-21 | 0% | bar: Sat 256 to Mon 258
131 | Install electrical finishes & lighting |  | 2021-06-19 | 2 | 2021-06-21 | 0% | bar: Sat 256 to Mon 258
132 | Install vac machine & cover plates |  | 2021-06-19 | 1 | 2021-06-20 | 0% | bar: Sat 256 to Sun 257
133 | Install media systems finishes |  | 2021-06-19 | 2 | 2021-06-21 | 0% | bar: Sat 256 to Mon 258
134 | Install shower glass & mirrors |  | 2021-06-07 | 3 | 2021-06-10 | 0% | bar: Mon 244 to Thu 247
135 | Install door & bath hardware |  | 2021-06-16 | 1 | 2021-06-17 | 0% | bar: Wed 253 to Thu 254
136 | Install floor finishes carpet / hardwood |  | 2021-06-16 | 6 | 2021-06-22 | 0% | bar: Wed 253 to Tue 259
137 | Deliver appliances |  | 2021-06-22 | 1 | 2021-06-23 | 0% | bar: Tue 259 to Wed 260
138 | Baseboard other installation |  | 2021-06-22 | 2 | 2021-06-24 | 0% | bar: Tue 259 to Thu 261
139 | Install appliances |  | 2021-06-23 | 2 | 2021-06-25 | 0% | bar: Wed 260 to Fri 262
140 | Final Plumbing & HVAC inspections |  | 2021-06-23 | 2 | 2021-06-25 | 0% | bar: Wed 260 to Fri 262
141 | Final Electrical inspections |  | 2021-06-23 | 2 | 2021-06-25 | 0% | bar: Wed 260 to Fri 262
142 | Rough initial home clean |  | 2021-06-25 | 1 | 2021-06-26 | 0% | bar: Fri 262 to Sat 263
143 | Furnace duct cleaning |  | 2021-06-26 | 1 | 2021-06-27 | 0% | bar: Sat 263 to Sun 264
144 | Final home clean |  | 2021-06-27 | 1 | 2021-06-28 | 0% | bar: Sun 264 to Mon 265
PHASE TWELVE FINAL EXTERIOR WORK
145 | Final grade |  | 2021-06-25 | 2 | 2021-06-27 | 0% | bar: Fri 262 to Sun 264
146 | Patios & Sidewalks |  | 2021-06-27 | 3 | 2021-06-30 | 0% | bar: Sun 264 to Wed 267
147 | Trees & shrubs installed |  | 2021-06-30 | 3 | 2021-07-03 | 0% | bar: Wed 267 to Sat 270
148 | Top-soil-Loam |  | 2021-07-03 | 2 | 2021-07-05 | 0% | bar: Sat 270 to Mon 272
149 | Grass seed / sod |  | 2021-07-05 | 2 | 2021-07-07 | 0% | bar: Mon 272 to Wed 274
150 | Fencing |  | 2021-06-27 | 3 | 2021-06-30 | 0% | bar: Sun 264 to Wed 267
| FINAL COMPLETE HOME DRAW |  | 2021-06-27 |  | 2021-06-27 | 0% | bar: Sun 264
TURN OVER TO CLIENT
151 | Notice of substantial complete posted | * | 2021-06-28 | 1 | 2021-06-29 | 0% | bar: Mon 265 to Tue 266
152 | Final occupancy inspection by approving authorities |  | 2021-06-29 | 1 | 2021-06-30 | 0% | bar: Tue 266 to Wed 267
153 | New Home Warranty inspections |  | 2021-06-30 | 1 | 2021-07-01 | 0% | bar: Wed 267 to Thu 268
154 | Lien hold back time started |  | 2021-07-01 | 1 | 2021-07-02 | 0% | bar: Thu 268 to Fri 269
155 | Punch list inspection done |  | 2021-07-02 | 1 | 2021-07-03 | 0% | bar: Fri 269 to Sat 270
156 | Final service work and punch list completed |  | 2021-07-03 | 7 | 2021-07-10 | 0% | bar: Sat 270 to Sat 277
MOVE-IN

## Sheet3
| WEEKLY GANTT CHART | [5 empty] | Wed | Wed | Wed | Wed | Wed | Wed | Wed | Wed | Wed | Wed | Wed | Wed | Wed | Wed | Wed | Wed | Wed | Wed | Wed | Wed | Wed | Wed | Wed | Wed | Wed | Wed | Wed | Wed | Wed | Wed | Wed | Wed | Wed | Wed | Wed | Wed | Wed | Wed | Wed | Wed | Wed | Wed | Wed | Wed | Wed
| For: Mr. & Mrs. |  |  |  | # of days |  | 6 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45
| PROJECT LOCATION: |  | Start Date | Duration | End Date | % Done | 2020-10-07 | 2020-10-14 | 2020-10-21 | 2020-10-28 | 2020-11-04 | 2020-11-11 | 2020-11-18 | 2020-11-25 | 2020-12-02 | 2020-12-09 | 2020-12-16 | 2020-12-23 | 2020-12-30 | 2021-01-06 | 2021-01-13 | 2021-01-20 | 2021-01-27 | 2021-02-03 | 2021-02-10 | 2021-02-17 | 2021-02-24 | 2021-03-03 | 2021-03-10 | 2021-03-17 | 2021-03-24 | 2021-03-31 | 2021-04-07 | 2021-04-14 | 2021-04-21 | 2021-04-28 | 2021-05-05 | 2021-05-12 | 2021-05-19 | 2021-05-26 | 2021-06-02 | 2021-06-09 | 2021-06-16 | 2021-06-23 | 2021-06-30 | 2021-07-07 | 2021-07-14 | 2021-07-21 | 2021-07-28 | 2021-08-04 | 2021-08-11
PHASE ONE - PLANNING & START-UP
1 | Close on Land building site purchase |  | 2020-10-07 | 1 | 2020-10-08 | 25% | bar: 6
2 | Verify Construction Funding |  | 2020-10-07 | 1 | 2020-10-08 | 0% | bar: 6
3 | Architectural planning |  | 2020-10-08 | 14 | 2020-10-22 | 0% | bar: 2 to 3
4 | Structural Drawings |  | 2020-10-22 | 18 | 2020-11-09 | 0% | bar: 4 to 5
5 | Set detailed building specifications |  | 2020-11-09 | 3 | 2020-11-12 | 0% | bar: 6
6 | Have Client make all selections |  | 2020-11-12 | 7 | 2020-11-19 | 0% | bar: 7
7 | Client approves plans, spec's, and budget |  | 2020-11-19 | 3 | 2020-11-22 | 0%
8 | Make any requested plan & spec's changes |  | 2020-11-26 | 10 | 2020-12-06 | 0% | bar: 9
9 | Modify plans & spec's to meet any revisions |  | 2020-12-06 | 5 | 2020-12-11 | 0% | bar: 10
0%
| PHASE TWO - TENDER-BIDS & CONTRACTS |  |  |  |  | 0%
10 | Make copies of all plans & spec's |  | 2020-12-11 | 1 | 2020-12-12 | 0%
11 | Distribute plans & spec's to trades & suppliers |  | 2020-12-12 | 5 | 2020-12-17 | 0% | bar: 11
12 | Tender project / quotes |  | 2020-12-17 | 15 | 2021-01-01 | 0% | bar: 12 to 13
13 | Review Tenders & bids / quotes |  | 2021-01-01 | 5 | 2021-01-06 | 0% | bar: 14
14 | Approve construction budget / quote |  | 2021-01-01 | 3 | 2021-01-04 | 0%
15 | Execute Subcontractor agreements |  | 2021-01-04 | 4 | 2021-01-08 | 0% | bar: 14
16 | Walk lot with owner before construction |  | 2021-01-04 | 1 | 2021-01-05 | 0%
0%
| UPFRONT DEPOIST DRAW |  | 2021-01-05 |  | 2021-01-05 | 0%
0%
| PHASE THREE - APPROVING ATHOURITIES |  |  |  |  | 0%
17 | Apply for Development Permits? | * | 2020-12-11 | 0 | 2020-12-11 | 0%
18 | APPLY FOR BUILDING PERMITS | * | 2020-12-11 | 15 | 2020-12-26 | 0% | bar: 11 to 12
19 | BUILDING PERMIT APPROVALS | * | 2020-12-26 | 1 | 2020-12-27 | 0%
20 | Construction liabilty insurance |  | 2020-12-27 | 1 | 2020-12-28 | 0%
21 | Order window package |  | 2020-12-26 | 1 | 2020-12-27 | 0%
22 | Order roof trusses & floor joist |  | 2020-12-26 | 1 | 2020-12-27 | 0%
23 | Get lumber order ready |  | 2020-12-26 | 1 | 2020-12-27 | 0%
24 | Schedule Surveyor |  | 2020-12-26 | 1 | 2020-12-27 | 0%
25 | Schedule excavation |  | 2020-12-26 | 1 | 2020-12-27 | 0%
26 | Prep building site "Clearing or strip top-soil" |  | 2020-12-26 | 3 | 2020-12-29 | 0%
27 | Select & Schedule cribbing crew |  | 2020-12-26 | 1 | 2020-12-27 | 0%
28 | Select & schedule framing crew |  | 2020-12-26 | 1 | 2020-12-27 | 0%
0%
| PHASE FOUR - SITE PREP |  |  |  |  | 0%
29 | Clear lot of top soils / tress etc. (stock pile loam) | * | 2020-12-27 | 2 | 2020-12-29 | 0%
30 | Surveyor pin site for excavation | * | 2020-12-29 | 1 | 2020-12-30 | 0% | bar: 13
31 | Excavate site | * | 2020-12-30 | 3 | 2021-01-02 | 0% | bar: 13
32 | Excavate sewer & Water |  | 2021-01-02 | 1 | 2021-01-03 | 0%
33 | Excavate electrical service |  | 2021-01-03 | 1 | 2021-01-04 | 0%
34 | Surveyor pin excavation for footings | * | 2021-01-02 | 1 | 2021-01-03 | 0%
35 | Deliver Lumber and rebar for foundation work |  | 2021-01-03 | 1 | 2021-01-04 | 0%
36 | Hook-up Temporary construction power |  | 2021-01-04 | 1 | 2021-01-05 | 0%
0%
| PHASE FIVE - FOUNDATION |  |  |  |  | 0%
37 | Install footing forms |  | 2021-01-03 | 3 | 2021-01-06 | 0% | bar: 14
38 | Inspect footings |  | 2021-01-06 | 1 | 2021-01-07 | 0% | bar: 14
39 | Order concrete & pump for footing pour |  | 2021-01-07 | 1 | 2021-01-08 | 0%
40 | Surveyor to pin top of footing |  | 2021-01-08 | 1 | 2021-01-09 | 0%
41 | Install foundation forms |  | 2021-01-09 | 3 | 2021-01-12 | 0%
42 | Order concrete & pump for wall pour |  | 2021-01-12 | 1 | 2021-01-13 | 0% | bar: 15
43 | Concrete pour foundation |  | 2021-01-12 | 2 | 2021-01-14 | 0% | bar: 15
44 | Strip foundation |  | 2021-01-14 | 1 | 2021-01-15 | 0%
45 | Order and install foundation seal |  | 2021-01-15 | 1 | 2021-01-16 | 0%
46 | Foundation drainage gravel & weeping tile |  | 2021-01-16 | 1 | 2021-01-17 | 0%
47 | Foundation inspection by approving authorities |  | 2021-01-17 | 2 | 2021-01-19 | 0%
48 | Install sewer, water, and electrical service |  | 2021-01-16 | 2 | 2021-01-18 | 0%
49 | Install main electric panel c/w with temp power outlets |  | 2021-01-15 | 1 | 2021-01-16 | 0%
50 | Inspection of service installations |  | 2021-01-16 | 1 | 2021-01-17 | 0%
0%
| FOUNDATION DRAW |  | 2021-01-17 |  | 2021-01-17 | 0%
0%
51 | Back-fill foundation | * | 2021-01-17 | 2 | 2021-01-19 | 0%
52 | Order main lumber package |  | 2021-01-19 | 1 | 2021-01-20 | 0% | bar: 16
53 | Order Garbage bin to site |  | 2021-01-20 | 1 | 2021-01-21 | 0% | bar: 16
54 | Order Porta-can toilet to site |  | 2021-01-21 | 1 | 2021-01-22 | 0%
55 | Select and schedule fire place contractor |  | 2021-01-19 | 1 | 2021-01-20 | 0% | bar: 16
56 | Select and schedule roofing contractor |  | 2021-01-19 | 1 | 2021-01-20 | 0% | bar: 16
57 | Select and schedule siding contractor |  | 2021-01-19 | 1 | 2021-01-20 | 0% | bar: 16
58 | Select and schedule soffit & gutter contractor |  | 2021-01-19 | 1 | 2021-01-20 | 0% | bar: 16
59 | Select and schedule Plumbing Contractor |  | 2021-01-19 | 1 | 2021-01-20 | 0% | bar: 16
60 | Select and schedule HVAC contractor |  | 2021-01-19 | 1 | 2021-01-20 | 0% | bar: 16
61 | Select and schedule Electrical contractor |  | 2021-01-19 | 1 | 2021-01-20 | 0% | bar: 16
62 | Select & schedule Insulation & drywall contractor |  | 2021-01-19 | 1 | 2021-01-20 | 0% | bar: 16
63 | Select and schedule Vacuum contractor |  | 2021-01-19 | 1 | 2021-01-20 | 0% | bar: 16
0%
| PHASE SIX - MAIN BUILDING STRUCTUER |  |  |  |  | 0%
64 | Deliver framing lumber package |  | 2021-01-23 | 1 | 2021-01-24 | 0%
65 | Start framing crew |  | 2021-01-24 | 4 | 2021-01-28 | 0% | bar: 17
66 | Main sub floor completed |  | 2021-01-28 | 4 | 2021-02-01 | 0%
67 | Main floor walls completed |  | 2021-02-01 | 5 | 2021-02-06 | 0% | bar: 18
68 | Deliver roof trusses |  | 2021-02-06 | 1 | 2021-02-07 | 0%
69 | Second floor sub floor completed |  | 2021-02-07 | 4 | 2021-02-11 | 0% | bar: 19
70 | Order stairs |  | 2021-02-11 | 1 | 2021-02-12 | 0%
71 | Second floor walls completed |  | 2021-02-12 | 5 | 2021-02-17 | 0% | bar: 20
72 | Deliver windows and ex doors |  | 2021-02-17 | 1 | 2021-02-18 | 0% | bar: 20
73 | Order garage overhead doors |  | 2021-02-18 | 1 | 2021-02-19 | 0%
74 | Deliver & Install stairs |  | 2021-02-19 | 2 | 2021-02-21 | 0%
75 | HVAC mark-out |  | 2021-02-21 | 3 | 2021-02-24 | 0% | bar: 21
76 | Cut-out HVAC holes by framer |  | 2021-02-24 | 4 | 2021-02-28 | 0% | bar: 21
77 | Framing roof on lock-up stage | * | 2021-02-28 | 10 | 2021-03-10 | 0% | bar: 22 to 23
78 | Prep & Pour basement concrete slab (See R-in-fl-heat) |  | 2021-03-10 | 4 | 2021-03-14 | 0% | bar: 23
79 | Framing basement development |  | 2021-03-14 | 8 | 2021-03-22 | 0% | bar: 24
80 | Framing inspections & engineering inspections |  | 2021-03-22 | 3 | 2021-03-25 | 0% | bar: 25
0%
| LOCK-UP STAGE DRAW |  | 2021-03-23 |  | 2021-03-23 | 0%
0%
| PHASE SEVEN - MECANICAL ROUGH-IN |  |  |  |  | 0%
81 | Do electrical walk-through with owner |  | 2021-03-25 | 1 | 2021-03-26 | 0%
82 | Install rough-in plumbing (FIRST order) |  | 2021-03-26 | 4 | 2021-03-30 | 0%
83 | Install rough-in HVAC (SECOND order) |  | 2021-03-30 | 4 | 2021-04-03 | 0% | bar: 26
84 | Install fire place's (rough-in) |  | 2021-04-03 | 1 | 2021-04-04 | 0%
85 | Install rough-in electrical & media systems (THIRD order) |  | 2021-04-04 | 4 | 2021-04-08 | 0% | bar: 27
86 | Install rough-in central vacuum (After electrical) |  | 2021-04-08 | 1 | 2021-04-09 | 0%
87 | Install security rough-ins |  | 2021-04-09 | 2 | 2021-04-11 | 0%
88 | Alarm rough-ins |  | 2021-04-11 | 1 | 2021-04-12 | 0%
89 | Set up for temporary heat (winter construction) |  | 2021-04-12 | 1 | 2021-04-13 | 0%
90 | Rough-in mechanical inspections | * | 2021-04-13 | 3 | 2021-04-16 | 0% | bar: 28
91 | Final framing check and adjustments |  | 2021-04-16 | 3 | 2021-04-19 | 0%
0%
| PHASE EHIGHT - EXTERIOR FINISHES |  |  |  |  | 0%
92 | Install roofing | * | 2021-04-04 | 4 | 2021-04-08 | 0% | bar: 27
93 | Build decks & deck railing |  | 2021-04-04 | 6 | 2021-04-10 | 0% | bar: 27
94 | Install garage concrete slab |  | 2021-04-04 | 1 | 2021-04-05 | 0%
95 | Install exterior masonry / cultured stone |  | 2021-04-04 | 6 | 2021-04-10 | 0% | bar: 27
96 | Install exterior soffit & facia |  | 2021-04-04 | 2 | 2021-04-06 | 0%
97 | Install exterior siding, trim / stucco |  | 2021-04-06 | 7 | 2021-04-13 | 0% | bar: 27
98 | Paint exterior trim |  | 2021-04-13 | 3 | 2021-04-16 | 0% | bar: 28
99 | Install garage over head doors & openers |  | 2021-04-09 | 3 | 2021-04-12 | 0%
100 | Install drive way / patio concrete slab |  | 2021-04-12 | 3 | 2021-04-15 | 0% | bar: 28
101 | Select and schedule cabinets |  | 2021-04-12 | 1 | 2021-04-13 | 0%
102 | Select and schedule finishing crew |  | 2021-04-12 | 1 | 2021-04-13 | 0%
103 | Select and schedule int. railing installer |  | 2021-04-12 | 1 | 2021-04-13 | 0%
104 | Select and schedule int. flooring contractors |  | 2021-04-12 | 1 | 2021-04-13 | 0%
0%
| PHASE NINE - DRYWALL STAGE |  |  |  |  | 0%
105 | Install batt insulation & VB |  | 2021-04-19 | 3 | 2021-04-22 | 0% | bar: 29
106 | Caulk & air-seal, draft & fire stop |  | 2021-04-22 | 1 | 2021-04-23 | 0%
107 | Insulation inspection (before cover-up) |  | 2021-04-23 | 1 | 2021-04-24 | 0%
108 | Install drywall board |  | 2021-04-24 | 5 | 2021-04-29 | 0% | bar: 30
109 | Install blow-in attic insulation |  | 2021-04-29 | 1 | 2021-04-30 | 0%
110 | Order and schedule millwork packaged |  | 2021-04-30 | 1 | 2021-05-01 | 0%
111 | Select and schedule painting contractor |  | 2021-05-01 | 1 | 2021-05-02 | 0%
112 | Drywall mud & tapping |  | 2021-04-30 | 6 | 2021-05-06 | 0% | bar: 31
113 | Drywall sanding |  | 2021-05-06 | 1 | 2021-05-07 | 0%
114 | Texture ceiling or level 5 ceiling |  | 2021-05-07 | 1 | 2021-05-08 | 0%
115 | Prime paint drywall | * | 2021-05-08 | 1 | 2021-05-09 | 0%
116 | Select and order appliances |  | 2021-05-08 | 1 | 2021-05-09 | 0%
117 | Select and order lighting fixtures |  | 2021-05-08 | 1 | 2021-05-09 | 0%
0%
| DRYWALL COMPLETE DRAW |  | 2021-05-09 |  | 2021-05-09 | 0%
0%
| PHASE TEN - INTERIOR FINIDHING STAGE |  |  |  |  | 0%
118 | Select and order all ceramic tile |  | 2021-05-09 | 1 | 2021-05-10 | 0%
119 | Deliver int. Millwork Package |  | 2021-05-09 | 1 | 2021-05-10 | 0%
120 | Install millwork & finish carpentry |  | 2021-05-10 | 14 | 2021-05-24 | 0% | bar: 32 to 33
121 | Install int. railing |  | 2021-05-10 | 4 | 2021-05-14 | 0% | bar: 32
122 | Install cabinets |  | 2021-05-10 | 6 | 2021-05-16 | 0% | bar: 32
123 | Template and order counter tops |  | 2021-05-16 | 2 | 2021-05-18 | 0%
124 | Install counter tops |  | 2021-05-28 | 2 | 2021-05-30 | 0%
125 | Install wall and floor ceramic tile |  | 2021-05-30 | 5 | 2021-06-04 | 0% | bar: 35
126 | Order shower enclosures |  | 2021-06-04 | 1 | 2021-06-05 | 0%
127 | Drywall touch-up for painter |  | 2021-06-05 | 1 | 2021-06-06 | 0%
128 | Painting interior millwork & walls |  | 2021-06-06 | 10 | 2021-06-16 | 0% | bar: 36 to 37
0%
| PHASE ELEVIN - FINAL STAGE |  |  |  |  | 0%
129 | Install bathroom flooring |  | 2021-06-16 | 3 | 2021-06-19 | 0% | bar: 37
130 | Install plumbing finishes / toilets |  | 2021-06-19 | 2 | 2021-06-21 | 0%
131 | Install electrical finishes & lighting |  | 2021-06-19 | 2 | 2021-06-21 | 0%
132 | Install vac machine & cover plates |  | 2021-06-19 | 1 | 2021-06-20 | 0%
133 | Install media systems finishes |  | 2021-06-19 | 2 | 2021-06-21 | 0%
134 | Install shower glass & mirrors |  | 2021-06-07 | 3 | 2021-06-10 | 0% | bar: 36
135 | Install door & bath hardware |  | 2021-06-16 | 1 | 2021-06-17 | 0% | bar: 37
136 | Install floor finishes carpet / hardwood |  | 2021-06-16 | 6 | 2021-06-22 | 0% | bar: 37
137 | Deliver appliances |  | 2021-06-22 | 1 | 2021-06-23 | 0% | bar: 38
138 | Baseboard other installation |  | 2021-06-22 | 2 | 2021-06-24 | 0% | bar: 38
139 | Install appliances |  | 2021-06-23 | 2 | 2021-06-25 | 0% | bar: 38
140 | Final Plumbing & HVAC inspections |  | 2021-06-23 | 2 | 2021-06-25 | 0% | bar: 38
141 | Final Electrical inspections |  | 2021-06-23 | 2 | 2021-06-25 | 0% | bar: 38
142 | Rough initial home clean |  | 2021-06-25 | 1 | 2021-06-26 | 0%
143 | Furnace duct cleaning |  | 2021-06-26 | 1 | 2021-06-27 | 0%
144 | Final home clean |  | 2021-06-27 | 1 | 2021-06-28 | 0%
0%
| PHASE TWELVE FINAL EXTERIOR WORK |  |  |  |  | 0%
145 | Final grade |  | 2021-06-25 | 2 | 2021-06-27 | 0%
146 | Patios & Sidewalks |  | 2021-06-27 | 3 | 2021-06-30 | 0% | bar: 39
147 | Trees & shrubs installed |  | 2021-06-30 | 3 | 2021-07-03 | 0% | bar: 39
148 | Top-soil-Loam |  | 2021-07-03 | 2 | 2021-07-05 | 0%
149 | Grass seed / sod |  | 2021-07-05 | 2 | 2021-07-07 | 0% | bar: 40
150 | Fencing |  | 2021-06-27 | 3 | 2021-06-30 | 0% | bar: 39
0%
| FINAL COMPLETE HOME DRAW |  | 2021-06-27 |  | 2021-06-27 | 0%
0%
| TURN OVER TO CLIENT |  |  |  |  | 0%
151 | Notice of substantial complete posted | * | 2021-06-28 | 1 | 2021-06-29 | 0%
152 | Final occupancy inspection by approving authorities |  | 2021-06-29 | 1 | 2021-06-30 | 0% | bar: 39
153 | New Home Warranty inspections |  | 2021-06-30 | 1 | 2021-07-01 | 0% | bar: 39
154 | Lien hold back time started |  | 2021-07-01 | 1 | 2021-07-02 | 0%
155 | Punch list inspection done |  | 2021-07-02 | 1 | 2021-07-03 | 0%
156 | Final service work and punch list completed |  | 2021-07-03 | 7 | 2021-07-10 | 0% | bar: 40
| MOVE-IN | [50 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X